## DEFECT TRACKER
Defect /Issue Report
|  |  | User Impact | Business impact
Status | Count | 1-Critical | 1 | 2
1-New | 2 | 2-High | 2 | 2
2-Open | 4 | 3-Medium | 3 | 0
3-Closed | 0 | 4-Low | 0 | 2
TOTALS | 6 |  | 6 | 6
Defect ID | Detected Date | Status | H/M/L User impact | H/M/L Business impact | Subject | Reported by | Defect / issue description | Environment | Customer facing update | Internal Update | Assigned to
1 | 2022-10-09 | 1-New | 2-High | 2-High | CRM connector: Email address gives error when saving. | Customer test team | Search for a relation (with email address) in the connector. Select relation. Confirm your choice. Enter empty fields. Click save and close Expected: Relation will be stored and closed Observed behavior: Error message | QA | With Engineer for review. | Check there isn't a conflict between test data email addresses and live addresses imported via the connector. | Engineer
2 | 2022-12-09 | 2-Open | 3-Medium | 4-Low | Need button to clear all fields. | Customer test team | The connector tab contains 8 search fields. I'm missing a button here to clear all fields for a new search. | Dev | New requirement. Workaround is to manually clear the fields. Engineer is assessing the effort. | Likely to be several days work. Will provide an estimate of effort to the customer. | PM & Engineer for LOE
3 | 2020-12-30 | 2-Open | 3-Medium | 2-High | Nationality is not given correctly. | Customer test team | Insured person (policy member) - nationality is not coming through connector. | QA | With Engineer for review. | Nationality data is in data import so should be coming through. | Engineer
4 | 16/9/2022 | 2-Open | 2-High | 1-Critical | Insured view shows 0 in policy tab. | Customer test team | Connector: Customer view Insured gives result 0 at Policy tab. | Dev | Related to “Link between Policy owner and Policy member not available”. | Looking at the XML data it seems that this member is not a policy owner, so the policy data is not in the XML. We need to see if we can add these memberships (as part of a change request). | Engineer
5 | 18/9/2022 | 2-Open | 3-Medium | 4-Low | Change search for Group Contract. | Customer project team | Search for Group Contract needs to return associated organisation record. At the moment the reference no. is returned. | QA | New requirement. Consider for future phase. | Raising a change request. Work around - show the organisation under group contract and drill down on the organisation for details. | PM & Engineer for LOE
6 | 20/9/2022 | 1-New | 1-Critical | 1-Critical | Login problems | Customer test team | Some login ID are not working properly . Not getting all the features in those login ID | QA | With Engineer for review. | Looking in the database for the LOGIN ID preferences and updating the list in 1 working day . | Engineer & PM

## Dropdowns
Status
1-New
2-Open
3-Closed
[Blank]
Severity
1-Critical
2-High
3-Medium
4-Low
[Blank]